# TFP evaluation for a baseline study

I have been analysing the TFP overall Logframe and the Concept Note to start to think about what needs to be measured as part of the baseline study to be conducted before the Programme begins. I have yet to work on the documents for each of Kiribati and Sierra Leone projects, but thought it worth starting a discussion on some of the ideas that my first analysis uncovered. These are early ideas, but they reveal that there is a collective need to clarify some of the central concepts in the programme (e.g. of problem-based learning) so that instruments can be created that will measure the occurance (or not) of what is seen as central to the TFP.

I have adopted the usual nomenclature for logframes (Logical Frameworks) used by DFID, though I recognise that the TFP logframe does not fit directly with this, but it nevertheless provides a useful basis for what to measure and when we might expect improvements on the outcomes etc. The DFID guidance on logframes uses three levels of statements: impacts, outcomes and outputs (DFID, 2011). This represents an hierarchy, starting at the lowest level with outputs: these indicated the activities that the project will do (and hence measures that will indicate they have been done successfully; e.g. to train 500 teachers). The next level up are the outcomes, which indicate what the outputs produce in terms of change as a result of the outputs (e.g. improved classroom practice improved as a result of training of teachers). At the highest level are the impacts, which are the result of the outcomes (e.g. that improved classroom practice leads to better student learning). For each of these statements of impact, outcome and outputs, there are one or more indicators, i.e. more specific measures that can be subject to some kind of instrumentation (e.g. a test for student learning outcomes to indicate impact). DFID guidance has specific views about the number of impacts and outcomes that a project should have, but I have ignored this in what follows.

My analysis so far has revealed the indicators below at each of the impact and outcome levels (outputs are not so important for the baseline) and I have made some attempts at providing a measure that is seen to be possible and sensible (the basis of an indicator). I have also given different outcomes for the different targets groups, i.e. those who will be part of the output activities: teacher educators, teachers (including head teachers) and organisations.

## Impact

Student learning outcomes: secondary examinations (public); subject examinations (school)

Completion (of junior/senior secondary education)

## Outcomes

### Teacher educators

[No clear outcomes; the TFP Logframe says: teacher educators … demonstrating improvement in instructional practices, collaborative learning and monitoring of learning outcomes]

### Teachers

Classroom practice: collaborative learning (of students); problem-based learning; community linkage; environmental response; social inclusion.

Professional learning: collaboration (online through community of practice, including production and ‘use’ of microlearning material)

### Organisations

Implementing ODL and technology-enabled teacher development programmes

Additional policies, strategies and guidelines for ODL and technology-enabled learning developed / adapted

Additional organisations engaging in collaborative resource development, research and knowledge sharing for quality learning opportunities

Note that for the purposes of the baseline it is not necessary to measure any of these organisational outcomes as it can be assumed that any measure of indicators will be ‘zero’! We can come back to them at a later stage, when later stages of evaluation are reached.

## The task for the immediate future

The above impact and outcome indicators need much more clarity for any measure and instruments to be arrived at, so the task is to achieve this clarity.

## References

DFID (2011) Guidance on using the revised Logical Framework, London: Department for International Development.

For those familiar with DFID logframes then bear with me for the sake of those who are not.

Note that these connections of outputs producing outcomes and outcomes producing impacts come from the Theory of Change of the TFP.

Students are the ultimate beneficiaries of output activities but are not directly included in project activities, except through the work the Programme does with teachers.